## Risk Register
ENTERPRISE RISK REGISTER
Project: Applicant Assistant Chatbot System ¦ Prepared By: Tosin Tuwase, Compliance Analyst (Practice) ¦ Date: August 2026 ¦ Review Cycle: Quarterly ¦ Reference: DPIA-2026-001 / POL-SEC-2026-004
Honesty note: This is a practice risk register built on the author's final-year academic project (Applicant Assistant Chatbot System). It does not represent a live enterprise environment.
Risk ID | Risk Description | Inherent Likelihood | Inherent Impact | Inherent Risk Rating | Mitigating Control | Residual Risk Rating
RISK-001 | Unauthorized administrative access to the production PostgreSQL database leads to data manipulation or loss of system integrity. | Medium | High | High | Implement strict Role-Based Access Control (RBAC), enforce Multi-Factor Authentication (MFA) for all database admins, and mandate quarterly access reviews. [Ref: POL-SEC-2026-004, S.4.1, S.4.3 & S.4.5] | Low
RISK-002 | Exfiltration or leakage of sensitive applicant personal data (Names, Emails, Phone Numbers) due to unencrypted data transmission or storage layers. | Medium | High | High | Enforce AES-256 encryption for data-at-rest within the cloud database and implement TLS 1.3 encryption for all data-in-transit. [Ref: DPIA-2026-001, S.5.1 & S.5.2] | Low
RISK-003 | Prolonged system downtime or service unavailability caused by a Distributed Denial of Service (DDoS) attack or infrastructure server overload. | High | Medium | High | Deploy cloud-native auto-scaling policies, utilize a Content Delivery Network (CDN) with DDoS protection, and establish automated load balancers. | Medium
RISK-004 | Threat actors exploit employee vulnerabilities via sophisticated phishing campaigns, compromising internal corporate credentials. | High | High | Critical | Deploy advanced automated email phishing filters, implement endpoint detection tools, and conduct mandatory bi-monthly security awareness training simulations. [Ref: POL-SEC-2026-004, S.4.2 & S.4.3] | Medium
RISK-005 | Inadvertent exposure of proprietary business data or corporate intellectual property through employee usage of unapproved public AI tools. | High | Medium | High | Configure corporate web proxies to block unauthorized AI platforms, publish an Acceptable Use Policy for AI tools, and provide approved enterprise-secured AI endpoints. | Low
RISK-006 | Indefinite retention of applicant PII due to failure to deploy the automated 180-day purge mechanism, violating the NDPA Storage Limitation principle. | Medium | High | High | Deploy the SQL cron-job purge script to the production environment immediately. Validate execution logs weekly. [Ref: DPIA-2026-001, S.5.3 — control defined but not yet implemented] | High
RISK-007 | Applicants are unable to access, correct, or request deletion of their stored personal data, violating NDPA data subject rights provisions. | Low | Medium | Medium | Implement a data subject rights request portal or formal email-based process. Acknowledge requests within 72 hours and resolve within 30 days. [Ref: DPIA-2026-001, S.5.4 — control defined but not yet implemented] | Medium
RISK RATING LEGEND
Critical |  | Immediate escalation required — board-level visibility
High |  | Senior management attention required — priority remediation
Medium |  | Management review required — scheduled remediation
Low |  | Acceptable — monitor at routine review cycles